## SOHS Maintenanc 2073-74
Council for Technical Education and Vocational Training
School of Health Science
Fiscal year: 2073/074 (2016/17)
cf=j=068/69
Annual Maintenance Plan 2016-17
S. No. | Particulars | Budget head | Estimate approval date | Estimate amount Rs.: | Method/ Process of Procurement | No. of package | Type of agreement | Documents of Tender, Quotation or Direct Purchase |  | Date of consent from CTEVT if requirded | Tender/ Quotation |  |  | Date of consent from CTEVT if requirded | Letter of intent and date of approval of Tender | Date of agreement of contract | Work start date | Work acomplishment date | Contractor/ Supplier |  |  | Remarks
[8 empty] | Preparation date | Approval date |  | Announcement date | Opening date | Evaluation completion date | [5 empty] | Name | Contract no. | Contract amount.
1 | Computer, Photocopy, Fax, Telephone and internet maintenance | 22212 | Shrawan 2073 | 150000 | DP | 5 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
2 | Plumbing, wiring maintenance | 22212 | Shrawan 2073 | 100000 | DP | 10 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
3 | Repair & maintenance Electricty pole,Transfermer,sub meter and Ac/Fan | 22212 | Shrawan 2073 | 25000 | DP | 3 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
4 | Maintenance of Generator | 22212 | Shrawan 2073 | 25000 | DP | 5 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
5 | Maintenance of Solar | 22212 | Shrawan 2073 | 10000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
6 | maintenance of Lab equipment | 22212 | Shrawan 2073 | 35000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
7 | Maintenance of vehicles | 22212 | Shrawan 2073 | 300000 | DP | 5 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
8 | Maintenance of furniture and Fixture | 22212 | Shrawan 2073 | 500000 | DP | 5 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
9 | Renovation of Guest House | 22321 | Shrawan 2073 | 1000000 | NCB | 2 | As Norms | Bhadra 2073 | Bhadra 2073 |  | Bhadra 2073 | Bhadra 2073 | [5 empty] | Jestha 2074 |  |  |  | not done
10 | Principal Quarter Painting & Maintenance | 22321 | Shrawan 2073 | 500000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | not done
11 | Maintenance of Hostel and office building | 22321 | Shrawan 2073 | 500000 | DP | 5 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
12 | Ramps construction of 2 House | 22321 | Shrawan 2073 | 50000 | DP | 1 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
13 | Clearance of bush area -emf*L km*fgL | 22212 | Shrawan 2073 | 25000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
14 | Maintenance of Road | 22212 | Shrawan 2073 | 150000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
15 | Repair of boundry fence | 22321 | Shrawan 2073 | 25000 | DP | 1 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | not done
16 | Maintenance of overhead tanks and pumps | 22321 | Shrawan 2073 | 360000 | DP | 2 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
17 | Maintenance of restroom and tank | 22321 | Shrawan 2073 | 150000 | DP | 10 | As Norms | Shrawan 2073 | Shrawan 2073 | [8 empty] | Jestha 2074 |  |  |  | done
| Prepared and Checked by: Ram Hari Khanal | [6 empty] | Checked by: Rabindra Acharya
| Signature:: | [6 empty] | Signature::
| Designation: Account Officer | [6 empty] | Designation: Vice Principal (Sanyojak Kharid Samiti)
| Date: 2073/03/26 | [7 empty] | Date: 2073/03/26