## SOHS Maintenanc 2075-76
Council for Technical Education and Vocational Training
School of Health Science
Fiscal year: 2074/075 (2017/18)
cf=j=068/69
Annual Maintenance Plan (2075 - 76) 2018-19
S. No. | Particulars | Budget head | Estimate approval date | Estimate amount Rs.: | Method/ Process of Procurement | No. of package | Type of agreement | Documents of Tender, Quotation or Direct Purchase |  | Date of consent from CTEVT if requirded | Tender/ Quotation |  |  | Date of consent from CTEVT if requirded | Letter of intent and date of approval of Tender | Date of agreement of contract | Work start date | Work acomplishment date | Contractor/ Supplier |  |  | Remarks
[8 empty] | Preparation date | Approval date |  | Announcement date | Opening date | Evaluation completion date | [5 empty] | Name | Contract no. | Contract amount.
1 | Computer, Photocopy, Fax, Telephone, networking and internet maintenance | 22212 | Shrawan 2074 | 150000 | DP | 5 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
2 | Plumbing, wiring maintenance | 22212 | Shrawan 2074 | 100000 | DP | 10 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2074
3 | Repair & maintenance Electricty pole,Transfermer,sub meter and Ac/Fan | 22212 | Shrawan 2074 | 25000 | DP | 3 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
4 | Maintenance of Generator | 22212 | Shrawan 2074 | 25000 | DP | 5 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
5 | maintenance of Lab equipment | 22212 | Shrawan 2074 | 35000 | DP | 2 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
6 | Mainenance of audio visual, scanner | 22212 | Shrawan 2074 | 500000 | DP |  | As Norms | Bhadra 2074 | Bhadra 2074 | [8 empty] | Jestha 2075
7 | Maintenance of website, basr code system | 22212 | Shrawan 2074 | 50000 | DP |  | As Norms | Bhadra 2074 | Bhadra 2074 | [8 empty] | Jestha 2075
8 | Maintenance of vehicles | 22212 | Shrawan 2074 | 300000 | DP | 5 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
9 | Maintenance of furniture and Fixture | 22212 | Shrawan 2074 | 500000 | DP | 5 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
10 | Maintenance of Herbal garden and greenary | 22321 | Shrawan 2074 | 1000000 | DP | 2 | As Norms | Bhadra 2074 | Bhadra 2074 | [8 empty] | Jestha 2075
11 | Principal Quarter Painting & Maintenance | 22321 | Shrawan 2074 | 500000 | DP | 2 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
12 | Maintenance of Hostel and office building | 22321 | Shrawan 2074 | 500000 | DP | 5 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
13 | Ramps construction of 2 House | 22321 | Shrawan 2074 | 50000 | DP | 1 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
14 | Clearance of bush area -emf*L km*fgL | 22212 | Shrawan 2074 | 25000 | DP | 2 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
15 | Maintenance of Road | 22212 | Shrawan 2074 | 150000 | DP | 2 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
16 | Maintenance of restroom and tank | 22321 | Shrawan 2074 | 150000 | DP | 10 | As Norms | Shrawan 2074 | Shrawan 2074 | [8 empty] | Jestha 2075
| Prepared and Checked by: Ram Hari Khanal | [6 empty] | Checked by: Raman Kumar Mehta
| Signature:: | [6 empty] | Signature::
| Designation: Account Officer | [6 empty] | Designation: Vice Principal (Sanyojak Kharid Samiti)
| Date: 2074/03/17 | [7 empty] | Date: 2074/03/17