## workplan QMU 2016-17
CTEVT
School of Health Science, Bharatpur
Bharatpur-10, Chitwan, Nepal
WORKPLAN QUALITY MANAGEMENT UNIT 2016-017
PDCA | Activities | Role of QMU | 2074 | [41 empty] | 2075
|  |  | Ashadh |  |  |  | Shrawan |  |  |  | Bhadra |  |  |  |  | Aswin |  |  |  | Kartik |  |  |  | Mangsir |  |  |  | Poush |  |  |  |  | Magh |  |  |  | Falgun |  |  |  | Chaitra |  |  |  | Baishakh |  |  |  | Jestha |  |  |  |  | Ashadh
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
PLAN | QIP Workbook | Update the Plan | bar: Ashadh 1 to Ashadh 4; Ashadh 52
| Annual Quality Improvement Objectives | Set Annual QIO | bar: Ashadh 1 to Bhadra 9
| QIO Action Plan | Prepare QIO Action Plan | bar: Ashadh 1 to Bhadra 9
| Ten Year Master Plan 2015 - 2024 | Update the Plan | bar: Ashadh 1 to Shrawan 5; Ashadh 52
| Strategic Plan 2015 - 019 | Update the Plan | bar: Ashadh 1 to Shrawan 5; Ashadh 52
| GESI action plan 2016 - 017 | Check whether Plan is formulated | bar: Ashadh 1 to Ashadh 4; Ashadh 52
| YPO 2016-017 | Check whether Plan is formulated | bar: Ashadh 1 to Ashadh 4; Ashadh 52
| Annual Maintenance Plan 2016 - 017 | Check whether Plan is formulated | bar: Ashadh 1 to Ashadh 4; Ashadh 52
| Workplan for PCU/ Academic Counselling | Check whether Plan is formulated | bar: Ashadh 1 to Shrawan 5
| Income Generation Plan 2016 - 017 | Check whether Plan is formulated | bar: Ashadh 1 to Ashadh 4; Ashadh 52
Do | According to Plans, Policies and Procedures | Inform and encourage all staffs about plans, policies and procedures, get their consent and make them to work effectively. Ensure each staff has a quality improvement objective. | bar: Ashadh 1 to Shrawan 5; Mangsir 22 to Mangsir 23; Ashadh 52 to Ashadh 53
CHECK | Review QIP Workbook | Make sure that QIP Workbook is reviewed and offer support | bar: Ashadh 1
| Review of QIO | Review progress | bar: Bhadra 9 to Jestha 51
| Review of QIP Action Plan | Review progress | bar: Bhadra 9 to Jestha 51
| Review Ten Year Master plan | Make sure thatTen Year Plan plan is reviewed and offer support | bar: Ashadh 1 to Shrawan 5
| Review Strategic Plan | Make sure that strategic plan is reviewed and offer support | bar: Ashadh 1 to Shrawan 5
| Check Implementation of GESI Action Plan | Support in checking whether all activities in GESI Action Plan are conducted in time | bar: Mangsir 23; Falgun 36; Baishakh 46; Ashadh 55
| Check Progress on YPO | Support in checking whether all activities in YPO are conducted in time | bar: Bhadra 13; Aswin 17; Kartik 21; Mangsir 25; Poush 30; Magh 34; Falgun 38; Chaitra 42; Baishakh 46; Jestha 51 to Ashadh 52; Ashadh 55
| Review Maintenance plan | Make sure that Maintenance Plan is reviewed and offer support | bar: Kartik 21; Falgun 38
| Review IG Plan | Make sure that IG Plan is reviewed and offer support | bar: Kartik 21; Falgun 38
| Check progress on Database | Check disaggregated data, charts and diagramme | bar: Bhadra 9 to Aswin 17
| Check progress on tracer study | Monitor Tracer study schedule | bar: Bhadra 11 to Mangsir 25
| Check Mgt Board meeting | Check frequency and quality | Bhadra 9: Meeting is called whenever needed, at least 4 times a year
| Check Mgt Committee meeting | Check frequency and quality | Bhadra 9: Meeting is called whenever needed, at least 6 times a year
| Check Staff Meeting | Check frequency and quality | bar: Bhadra 13; Aswin 17; Kartik 21; Mangsir 25; Poush 30; Magh 34; Falgun 38; Chaitra 42; Baishakh 46; Jestha 51 to Ashadh 52; Ashadh 55
| Check EAPC Meeting | Check frequency and quality | bar: Bhadra 10; Kartik 21; Mangsir 25; Poush 30; Baishakh 46
| Check QMU Meeting | Check frequency and quality | bar: Bhadra 13; Aswin 17; Kartik 21; Mangsir 25; Poush 30; Magh 34; Falgun 38; Chaitra 42; Baishakh 46; Jestha 51 to Ashadh 52; Ashadh 55
| MIS Unit | Check Unit is established | Magh 31: Establish unit
| Quality Management System | helps to establish and implement | Mangsir 22: With support from QIP volunteer
| Check Teacher's Diary | Check whether those are used as recommended | bar: Mangsir 23; Falgun 36; Baishakh 46; Ashadh 55
| QIP Audit | Prepare for Audit
ACT | Update QIP Workbook | Offer support to update | bar: Falgun 35 to Falgun 38
| Ten Year Master Plan 2015 - 2019 | Offer support to update | bar: Falgun 35 to Falgun 38
| Strategic Plan 2015 - 019 | Offer support to update | bar: Ashadh 1 to Ashadh 2; Ashadh 55
| GESI action plan 2016 - 017 | Provide suggestions for actions to be able to work | bar: Ashadh 1; Mangsir 23; Falgun 36; Baishakh 46; Ashadh 55
| YPO 2016-017 | Provide suggestions for actions to be able to work according YPO | bar: Bhadra 13; Aswin 17; Kartik 21; Mangsir 25; Poush 30; Magh 34; Falgun 38; Chaitra 42; Baishakh 46; Jestha 51 to Ashadh 52; Ashadh 55
| Annual Maintenance Plan 2016 - 017 | Provide suggestions for actions to be able to work | bar: Falgun 35 to Falgun 38
| Income Generation Plan 2016 - 017 | Provide suggestions for actions to be able to work | bar: Falgun 35 to Falgun 38
| Write recommendation based on Meetings | Propose recommendation to the Management | bar: Mangsir 23; Falgun 36; Baishakh 46; Ashadh 55
| Recommendation based on QIP Audit Report | Propose recommendation to the Management | bar: Shrawan 6; Ashadh 53