## Academic YPO 207374
CTEVT
School of Health Science, Bharatpur
Bharatpur-10, Chitwan, Nepal
YEARLY PLAN OF OPERATION
S. No. | Activities | Quantity | 2074 | [33 empty] | 2075 | [17 empty] | Responsible
|  |  | Bhadra |  |  |  |  | Aswin |  |  |  | Kartik |  |  |  | Mangsir |  |  |  | Poush |  |  |  |  | Magh |  |  |  | Falgun |  |  |  | Chaitra |  |  |  | Baishakh |  |  |  | Jestha |  |  |  |  | Ashadh |  |  |  | Shrawan
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | Students recruitment | Ashadh, Shrawan, Bhadra, Aswin for academic year 2074/75 | [52 empty] | SOHS, CTEVT
2 | Study block | 30 weeks | [52 empty] | P/VP/HOD
3 | Terminal/ class test | 3 weeks | [52 empty] | Teachers
4 | Comm./ Cli.Practicum | 6 months | [52 empty] | HOD (GM)
5 | Vacation | 6 weeks | [52 empty] | SOHS
6 | Nabin mem Blood donation | 1 day | [52 empty] | All*
7 | Medical Camps | 2 episodes | [52 empty] | P/VP/HOD
8 | Hospital Pr (CMLT) | 6 months | [52 empty] | HOD (MLT)
9 | Short-term trainings | 1 episode | [52 empty] | P/VP
10 | Profesional Fie. Pr. (DPh) | 1 week | [52 empty] | HOD (DPh)
11 | Botanical tour (DPh) | 1 week | [52 empty] | HOD (DPh)
12 | Industrial training | 1 week | [52 empty] | HOD (DPh)
13 | Community Pharmacy Pr | 4 weeks | [52 empty] | HOD (DPh)
14 | summer placement HA2nd | 10 weeks | [52 empty] | HOD (GM)
15 | summer placement lab, DPh | 4 weeks | [52 empty] | HODs
16 | Practical classes | 20 weeks | [52 empty] | HODs
17 | Std. progress review | 3 weeks | [52 empty] | P/VP/HODs
18 | Revision classes | 2 weeks | [52 empty] | HODs
19 | Field supervision | 6 months | [52 empty] | HODs
20 | Mndap & School day | Magh12 | [52 empty] | All*
21 | Final exam & its prep | 6 weeks | [52 empty] | P/VP/HODs
22 | Dashain & Tihar | 1 month
Activiites may vary according to circumstances
All* means P/vp/HODs, Teachers, Admin staffs, students
Vacation:
Summer Vacation: Ashadh 15- Shrawan 14
Winter Vacation: Poush 15 - Magh 1
Dashain, Tihar Vacation: Aswin 5 - Kartik 4

## Administrative YPO 207374
CTEVT
School of Health Science, Bharatpur
Bharatpur-10, Chitwan, Nepal
YEARLY PLAN OF OPERATION
S. No. | Activities | Quantity | 2074 | [33 empty] | 2075 | [17 empty] | Responsible
|  |  | Bhadra |  |  |  |  | Aswin |  |  |  | Kartik |  |  |  | Mangsir |  |  |  | Poush |  |  |  |  | Magh |  |  |  | Falgun |  |  |  | Chaitra |  |  |  | Baishakh |  |  |  | Jestha |  |  |  |  | Ashadh |  |  |  | Shrawan
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
A, | Marketing and Advertisement
1 | Notice in national magazines | three weeks | [52 empty] | P/VP | bar: Ashadh 44 to Ashadh 46
2 | Notice on school website | three weeks | [52 empty] | P/VP | bar: Ashadh 44 to Ashadh 46
3 | Prepare and distribute pamphlets | 5 weeks | [52 empty] | P/VP | bar: Ashadh 44 to Shrawan 48
4 | Create SOHS's Facebook page | 2 weeks | [52 empty] | P/VP | bar: Poush 21 to Poush 22
5 | Conduct workshops for publicity in different parts of Nepal | 2,5 months | [52 empty] | P/VP/HOD | bar: Baishakh 35 to Ashadh 45
6 | Update Citizen charter | 5 weeks | [52 empty] | P/VP/Admin | bar: Ashadh 44 to Shrawan 48
7 | Publish reports of tracer study and student evaluations in brochures | 1 month | [52 empty] | MIS Unit | bar: Baishakh 35 to Baishakh 38
B. | Application and Enrollment
1 | Collection of application forms | 5 weeks | [52 empty] | Examination unit | bar: Ashadh 44 to Shrawan 48
2 | Edit filled application form | 6 weeks | [52 empty] | Examination unit | bar: Ashadh 44 to Shrawan 49
3 | Enter application form in database | 6 weeks | [52 empty] | Examination unit | bar: Ashadh 44 to Shrawan 49
4 | Produce and distribute admit card | 2 weeks | [52 empty] | Examination unit | bar: Shrawan 48 to Shrawan 49
5 | Support CTEVT with entrance examination | 2 weeks | [52 empty] | P/VP | bar: Shrawan 48 to Shrawan 49
6 | Enrollment according to CTEVT guideline. | 6 weeks | [52 empty] | P/VP/Admin | bar: Bhadra 1 to Bhadra 5; Shrawan 52
7 | Enrollment to girls hostel according to school guidelines. | 13 weeks | [52 empty] | PCU | bar: Bhadra 5 to Mangsir 17
8 | Provide orientation to new teachers | Ongoing | [52 empty] | VP
9 | Provide orientation to students before new session and before fieldwork | 4 weeks | [52 empty] | VP/HOD | bar: Bhadra 4; Magh 23; Falgun 28; Jestha 40
C. | Academic activities
1 | Study block | 30 weeks | [52 empty] | P/VP/HOD | bar: Bhadra 3 to Ashadh 45
2 | Terminal/ class test | 3 weeks | [52 empty] | Teachers | bar: Mangsir 17; Poush 22; Chaitra 32
3 | Comm./ Cli.Practicum | 6 months | [52 empty] | HOD (GM) | bar: Magh 23 to Ashadh 47
4 | Vacation | 6 weeks | [52 empty] | SOHS | bar: Poush 21 to Poush 22; Jestha 42 to Ashadh 45
5 | Nabin mem Blood donation | 1 day | [52 empty] | All* | bar: Jestha 39
6 | Medical Camps | 2 episodes | [52 empty] | P/VP/HOD | bar: Chaitra 34 to Baishakh 35
7 | Hospital Pr (CMLT) | 6 months | [52 empty] | HOD (MLT) | bar: Magh 23 to Shrawan 48
8 | Short-term trainings | different episodes | [52 empty] | P/VP | bar: Mangsir 14 to Ashadh 45
9 | Profesional Fie. Pr. (DPh) | 1 week | [52 empty] | HOD (DPh) | bar: Falgun 27
10 | Botanical tour (DPh) | 1 week | [52 empty] | HOD (DPh) | bar: Poush 19
11 | Industrial training | 1 week | [52 empty] | HOD (DPh) | bar: Poush 20
12 | Community Pharmacy Pr | 4 weeks | [52 empty] | HOD (DPh) | bar: Falgun 29 to Chaitra 32
13 | summer placement HA2nd | 10 weeks | [52 empty] | HOD (GM) | bar: Jestha 41 to Shrawan 50
14 | summer placement lab, DPh | 4 weeks | [52 empty] | HODs | bar: Jestha 41 to Ashadh 44
15 | Practical classes | 20 weeks | [52 empty] | HODs | bar: Falgun 27 to Ashadh 47
16 | Std. progress review | 3 weeks | [52 empty] | P/VP/HODs | bar: Baishakh 37 to Baishakh 38
17 | Revision classes | 2 weeks | [52 empty] | HODs | bar: Shrawan 49 to Shrawan 50
18 | Field supervision | 8 months | [52 empty] | HODs | bar: Mangsir 14 to Ashadh 47
19 | Extra Curricular Activities: MNDAP, quiz, CTEVT day | Magh12 | [52 empty] | All* | bar: Magh 25
20 | Final exam & its prep | 4 weeks | [52 empty] | P/VP/HODs | bar: Bhadra 1 to Bhadra 2; Shrawan 51 to Shrawan 52
21 | Dashain & Tihar | 1 month | bar: Aswin 8 to Kartik 13
D. | Governance and Management
1 | School management board meeting | 4 times | Bhadra 1: Meeting is called whenever needed, at least 4 times a year | P
2 | School Management Committee Meeting | 6 times | Bhadra 1: Meeting is called whenever needed, at least 6 times a year | P/VP
3 | Staff meeting | 12 weeks | [52 empty] | P/VP | bar: Bhadra 5; Aswin 9; Kartik 13; Mangsir 17; Poush 22; Magh 26; Falgun 30; Chaitra 34; Baishakh 38; Jestha 43; Ashadh 47; Shrawan 52
4 | Review Strategic plan | 1 week | [52 empty] | P/VP | bar: Shrawan 52
5 | Review and update YPO's | 12 weeks | [52 empty] | P/VP/HOD | bar: Bhadra 5; Aswin 9; Kartik 13; Mangsir 17; Poush 22; Magh 26; Falgun 30; Chaitra 34; Baishakh 38; Jestha 43; Ashadh 47; Shrawan 52
6 | Write YPO's next year | 1 week | [52 empty] | P/VP/HOD | bar: Jestha 43
7 | QMU meetings | 12 weeks | [52 empty] | P/VP/HOD | bar: Bhadra 5; Aswin 9; Kartik 13; Mangsir 17; Poush 22; Magh 26; Falgun 30; Chaitra 34; Baishakh 38; Jestha 43; Ashadh 47; Shrawan 52
8 | MIS unit established /meetings | Three months | Magh 23: Establish unit | P/MIS Unit
9 | Quality management system developed and implemented | 9 month | Mangsir 14: With support from QIP volunteer | P/QMU
10 | Full implementation of digitalized attendance system | 9 month | [52 empty] | Admin | bar: Mangsir 14 to Shrawan 52
E. | Teaching and learning
1 | Quarterly checks of teacher's diary | 4 weeks | [52 empty] | VP/HOD | bar: Mangsir 15; Falgun 28; Baishakh 38; Shrawan 52
2 | Purchase required textbooks, journals and references for library | Three months | [52 empty] | VP/Library | bar: Mangsir 14 to Magh 26
3 | Update and ensure effective use of summer placement | 10 weeks | [52 empty] | VP/HOD | bar: Jestha 40 to Shrawan 49
4 | Develop format for supervision of classroom activities and conduct supervision | 10 times | Aswin 6: Develop format; Mangsir 14: Ten times for each HoD/vice-principal/principal | P/VP/HOD
5 | Evaluate curricula and send feedback to CTEVT | 5 weeks | [52 empty] | VP/HOD | bar: Bhadra 1 to Bhadra 5
F. | Support to students
1 | GESI action plan implemented | whole year | [52 empty] | P/GESI FP
2 | Develop ToR and work plan for PCU/academic counseling | Three months | [52 empty] | VP/PCU | bar: Aswin 6 to Mangsir 17
3 | Prepare and update list of potential employers | 1 month | [52 empty] | PCU/AC | bar: Bhadra 1 to Bhadra 4
4 | List potential universities to study after graduation | 1 month | [52 empty] | PCU/AC | bar: Bhadra 1 to Bhadra 4
5 | Encourage use of suggestion box | Ongoing | [52 empty] | P
G. | Teachers and Faculty
1 | Formulate and assign job descriptions to all staff | 3 months | [52 empty] | VP/PCU | bar: Bhadra 1 to Kartik 13
2 | Performance evaluation | 7 weeks | [52 empty] | P/VP/HOD | bar: Bhadra 1 to Bhadra 5; Jestha 39 to Jestha 40
3 | Writing individual performance improvement plans | 7 weeks | [52 empty] | P/VP/HOD | bar: Bhadra 1 to Bhadra 5; Jestha 39 to Jestha 40
4 | Review of staff's progress according development plans | 4 weeks | [52 empty] | P/VP/HOD | bar: Mangsir 15; Falgun 28; Baishakh 38; Shrawan 52
5 | Organize workshops to disseminate knowlegde and skills learned during training | Ongoing after training | [52 empty] | P/VP/HOD
6 | HRD unit established | 5 weeks | Kartik 10: Meetings planned as per need | P
H. | Budget and financial resources
1 | Review Revenue generation plan | 3 weeks | [52 empty] | P/VP/Account | bar: Kartik 13; Falgun 30; Ashadh 46
2 | Write Revenue generation plan next year | 2 weeks | [52 empty] | P/VP/Account | bar: Mangsir 17 to Poush 18
I. | Facilities and equipment
1 | Review Maintenance plan | 3 weeks | [52 empty] | P/VP/Store | bar: Kartik 13; Falgun 30; Ashadh 46
2 | Write new Facilities maintenance plan | 1 week | [52 empty] | P/VP/Store | bar: Shrawan 48
3 | Equip office, classrooms, laboratories and library with furniture, tools and equipment | Ongoing | Bhadra 1: We are shifting to new building and launching two new courses | P/VP/Store
4 | Construct botanical garden | 2 months | [52 empty] | P/VP/Store | bar: Bhadra 1 to Aswin 9
5 | Purchase schoolbus | 2 months | [52 empty] | P/VP/Store | bar: Bhadra 1 to Aswin 9
6 | Build ramps in remaining two buildings | 2 weeks | [52 empty] | P/VP/Store | bar: Poush 21 to Poush 22
J. | Linkages with industry
1 | Exposure visits for students to pharmaceuticals, botanical garden, water treatment plant, sewage disposal system | 4 weeks | [52 empty] | HOD | bar: Poush 19 to Poush 20; Falgun 27; Chaitra 31
2 | Meeting EAPC | 5 times | [52 empty] | P | bar: Bhadra 2; Kartik 13; Mangsir 17; Poush 22; Baishakh 38
K. | Research and development
1 | Update student and graduate database | 2 months | [52 empty] | P/VP/MIS Unit | bar: Bhadra 1 to Aswin 9
2 | Conduct tracer study | 15 weeks | [52 empty] | MIS Unit | bar: Bhadra 3 to Mangsir 17
3 | Program evaluations by students | 1 month | [52 empty] | MIS Unit | bar: Bhadra 1 to Bhadra 4
L. | Community Health Diagnosis, MHP and medical camp
1 | Request DPHO | 1 week | [52 empty] | HOD | bar: Kartik 13
2 | Conduct health diagnosis and MHP | 6 months | [52 empty] | HOD | bar: Magh 23 to Ashadh 47